## 工作表1
ID | ITEM | Owner | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE
General Planing & Design
0.1 | draw the website prototype | Product Owner | 10 | medium | done
0.2 | draw the navigation | Product Owner | 10 | medium | done
0.3 | design the whole system(API etc) | Product Owner | 10 | Hard | done
0.4 | design the function for website | Product Owner | 10 | Hard | done
0.5 | build the database | Product Owner | 6 | medium | done
0.6 | test all things | Product Owner | 1 | medium | to do
| Story#1 user create a new account |  |  |  |  | when the user sign up finish. the database have the user infomation
1.1 | Create sign up page for users | Product Owner | 5 | easy | done | the page have few field for user to fill up. indicate the incomplete information will alert the user. and finish the sign up will have success infomation
1.2 | add the account data to the database | Product Owner | 5 | easy | done | the infomation appear in the database
| Story#2 user login |  |  |  |  | User can use sign up infomation to sign in
2.1 | Create web page for uesr sign in | Product Owner | 6 | easy | done | a page have 2 field to let user fill in.
2.2 | Confirm the user is exists in database | Product Owner | 6 | easy | done | check the user wheather is exists
2.3 | Create session function | Product Owner | 6 | medium | done | Database create session cookie to user's browser if username and password matched
2.4 | Invaild data input alert | Product Owner | 5 | medium | done | Database check the data and jump the alter box
Story#3 User open trading function
3.1 | User have the trading infomation | Product Owner | 6 | medium | done | user can read some T and C then agree the T and C to accsee the trading account
3.2 | add User trading infomation to database | Product Owner | 6 | medium | done | user infomation display on database
Story #4 Leaderboard
4.1 | create leaderboard for customer | Product Owner | 5 | medium | done | user can see a list of all player on the list
4.2 | implement the backend data | Product Owner | 5 | medium | done
Story#5 User view the history for transfer
5.1 | User can see the history from the table | Product Owner | 6 | medium | done | user can see the trade history for own account
5.2 | link the database to show the shares history in the website table | Product Owner | 7 | hard | done
Story#6 User view the shares price
6.1 | Users can see the stock trends in real time(one hour update) | Product Owner | 7 | hard | done | stock price display on the list
6.2 | Implement backend to get the share price and put in the same row with shares | Product Owner | 7 | hard | done
Story #7: User view current balance and stock value
7.1 | create a box for current balance and stock value | Product Owner | 5 | medium | done | user can see his current balance and stcok value togather
7.2 | Connect the database to the foreground function | Product Owner | 7 | medium | done
Story #8: User wants to buy or sell stock
8.1 | create interface for buy stock | Product Owner | 6 | medium | done | user can buy the stock
8.2 | create interface for sell stock | Product Owner | 6 | medium | done | user can sell the stock
8.3 | update the database for user data | Product Owner | 8 | hard | done
Story #9: User view all stock in list
9.1 | create list for all stock | Product Owner | 6 | medium | done | user can see all the stcok from the list
9.3 | get data from API and show the data in list | Product Owner | 8 | hard | done
Story #10: user profile
10.1 | create the user information page | Product Owner | 6 | medium | done | user can view own information
10.2 | add edit fucntion for user | Product Owner | 6 | medium | done | user can edit the information
10.3 | update the database for user data | Product Owner | 6 | medium | done
Story #11: Add friend
11.1 | create the add friend fucntion | Product Owner | 6 | medium | done | user can add other customers
11.2 | create the interface of acception | Product Owner | 6 | medium | done | user can choose add friend or not
11.3 | record the relationship in the system | Product Owner | 6 | medium | done
Story #12: communication fucntion
12.1 | create the communication fucntion | Product Owner | 6 | medium | done | user can communicate to other friends
12.2 | create a message page | Product Owner | 6 | medium | done | user can write down the message to the friends
12.3 | create a message box | Product Owner | 8 | hard | done | user can view all messages
12.4 | record the message in the database | Product Owner | 7 | medium | done
Story #13 alarm system
13.1 | create the alarm page | Product Owner | 6 | medium | done | user can make alarm number
13.2 | create a alarm function | Product Owner | 6 | medium | done | user can get alarm eamil when the number over or low
Story #14: Admin login
14.1 | create admin login page | Product Owner | 5 | easy | done | admin can login the page
14.2 | create admin function for control user's funds | Product Owner | 6 | medium | done | admin can change user's funds etc
Story #15: user manage
15.1 | create user manage page | Product Owner | 5 | easy | done | admin can view the situation of users
15.2 | create add admin function | Product Owner | 6 | medium | done | admin can add one more managers
15.3 | create delete user function | Product Owner | 6 | medium | done | admin can delete the user
15.4 | create edit user information function | Product Owner | 6 | medium | done | admin can edit some information about users
15.5 | update change data in database | Product Owner | 6 | medium | done
Story #16:Testing
16.1 | Test all the thing and wrrite a testing report | Product Owner | 2 | medium | doing | test all the function and write down the bug
16.2 | Fix bugs | Product Owner | 8 | hard | doing | fix all the bug in report
16.3 | rewrrite the report | Product Owner | 3 | easy | doing | rewrite the bug report for how to fix the bug